## Sheet1
Daily Stand-up Meeting Report
Week: August 29th - September 2nd
Project Name: Nursing Symposium
Team Name: Team 7
| Monday | Wednesday | Friday
Anakapali Kanaka Venkata Phaneendra Babu | 1) I have did the initial research on the front end part and databases | 1) Looking the features to be presented | 1) Collected the functionalities
| 2) To discuss once again with the team regarding the process | 2) studying the code of existing api | 2) Task seggregation
| 3) I feel the clear information is still yet to finalize. | 3) studying the exixting apis | 3) Looking at the api and understanding the code
Sidhartha Gundarapu | 1) I accomplished this along with the team the title of the Project is Nursing Symposium and we got an overview regarding our project. | 1) As our team we have scheduled meeting with the client and this the accomplishment. | 1) As a team we have accomplished the outline of application development by having the client meeting. As a team we have accomplished the outline of application development by having the client meeting.
| 2) Ah, well I will do the required research on the project requirements after the client call. And I'm gonna discuss with the team and get the assigning of the work to all teammates as per their expertise. | 2) Well we are gonna have a client meeting and so we are having the team meeting regarding the information needed to develop the application as per the client requirements | 2) I have discussed and assigned the sprints with respect to the interests of the team mates.
| 3) The obstacles are regarding the clear info or requirements of the client and the development of application in IOS or Android background. | 3) As of now we don't have any obstacles as we are going to have a client meeting. | 3) The main obstacle regarding the decision of the application background is IOS or Android.
Phani Naidu Ratnala | 1) We had team meeting and decided the project name and by the collective review we are interested in doing the IOS application but it depends as per the client requirement. | 1) Gone through some references and great chat with the professor which I sorted some technical areas. | 1) Well had some good interaction with the client and came to known about the requirements also had some clarity now.
| 2) Will search for the references that are useful for my project | 2) We have client meeting today will have some quality time and we going to know which areas we should work on may be. | 2) Will start writing the basic code for user interface.
| 3) We actually don't know the exact requirements of the client. Once we came to know about the info we can start working on. | 3) I think no obstacles as of know. | 3) As of now no obstacles we going great and steady.
Alexander Dieringer | 1) Continued research into development methods for Android | 1) Mocked up a front page idea and a schedule view idea. They probably need to be iterated on post-meeting. | 1)
| 2) Today's goal is to mock up a few potential layouts the home & schedule pages in the application | 2) Figure out what type of layout is preferable for this type of app. Need to contact the client to coordinate the meeting. | 2) My plan for today is to update the repo with the stand up notes, to add any minutes from the client meeting we have, and to continue planning app design.
| 3) The main obstacle is that we have yet to meet our client and thus I don't really have a good idea about what features I should target | 3) The same obstacle as Monday, need to meet with the client to understand the functionalities & requirements. | 3) I was unable to meet at the specified time the two groups set with the client due to class. This means I have to read the meeting notes to decide my next steps.
Note:
1. What did I accomplish? 2.What will I do today? 3.What obstacles are impeding my progress?